## Strategy and Governance
Category | Solution # | Sub-category | Strategic goal | Action Plan | KPI | Priority MoSCoW | Estimated deadline | Responsible | Status
Strategy & Governance | 1 | x | Internal Governance | MSF Denmark is committed to mitigating our environmental impact by considering the environmental aspect in all decisions taken on consumption, guided by integration of sustainability lens in all policies. | MSF DK reduces its CO2 footprint by 50% by 2030 based on 2019 levels. | Must have | ONGOING | All in MSF DK | Done
|  |  |  | Annual reporting of footprint + progress on KPIs to MT and Board with recommendations to inform the coming strategy and budget for the next calendar year. (annual report) | MSF DK tracks its progress towards a 50% reduction by 2030. | Must have | Q2-3 - 2023 | Climate Advocacy Officer | Ongoing
|  |  |  | ToR approved ensuring clear mandate for MSF DK Green Team | MSF DK Green Team can work effectively with a clear mandate to support implementation of roadmap | Must have | 2023-06-01 | Climate Advocacy Officer | Pending
[9 empty] | Standby | To be discussed with Joaquim
[9 empty] | Cancelled | To be discussed with Joaquim
|  | y | Sustainability integrated into MSF DK Policies | Waste and Recycling Policy | MSF Denmark reduces waste and improves disposal of waste. | Must have |  | To be killed
|  |  |  | Travel Policy | MSF Denmark reduces CO2e associated with air travel. | Must have | Q4 - 2023 | Ole/HR rep | Done
|  |  |  | Procurement Policy (Vendors, Goods, Services, Financial services, delivery service, cleaning, energy) | MSF Denmark procures sustainably. | Must have |  | Eric | Done
|  |  |  | Sustainability guidelines for events, volunteer groups, external activities. |  | Must have |  | Climate Advocacy Officer
|  |  |  | IT policy |  | Must have | Q4-2023 | Christian
|  |  |  | Fundraising policy (paper use + purchasing) |  | Must have |  | Tania
|  | z | Monitoring, Reporting and Evaluating | Annual Plan for Green Team each year (activities, goals, meetings, educational activities, workshops) aligning with MSF DK strategy and budget. | Annual plan for 2024 created by Q4 2023. | Must have |  | Green Team
Improved EIT or carbon accounting resource to track CO2 emissions/waste
Quarterly evaluation of overall progress by Green Team + MT (annually for board, quarterly in perfomance report).
[6 empty] | Must have | Q1 - 2023
[6 empty] | Should have | Q2 - 2023
[6 empty] | Could have | Q3 - 2023
[6 empty] | Won't have | Q4 - 2023
Q1 - 2024
Q2 - 2024
Q3 - 2024
Q4 - 2024
Q1 - 2025
Q2 - 2025
Q3 - 2025
Q4 - 2025

## Network and relationships
Category | Solution # | Sub-category | Strategic goal | Action Plan | KPI | Priority MoSCoW | Estimated deadline | Green team Lead | Status
Network & relationships | 2 | x | Information sharing | Internal communication from the green team - quarterly updates in office meetings + ad hoc email updates | Raising awareness. | Should have | Ongoing | Project lead | Ongoing
|  |  |  | Information updates from our suppliers and vendors on their CO2 reduction plans (to relevant stakeholders) | Raising awareness. | Could have | Ongoing
|  |  |  | Stakeholder and change management processes with office staff in implementation of projects | Staff included in process. | Must have | Ongoing |  | Pending
|  | y | Community building | Nordic Green Team cooperation, team leads meet monthly | Shares resources and knowledge + support. | Should have | 2023-06-01 |  | Implemented
|  |  |  | Future collaboration between board green group and office green team, if relevant |  | Could have | Pending
|  |  |  | Work with Green Teams movement-wide |  | Should have | Ongoing |  | Ongoing
|  | z | External capacity | Vendors provide emissions (cross-referenced). | Assist in reporting and transparency. | Should have | Q1 - 2024 | Eric | Pending
|  |  |  | Use expertise from MSF DK Asso members, ie. Mauro + specialized profiles and their networks to assist in various areas | Expand reach and make use of missing expertise. | Could have | Ongoing
[6 empty] | Must have | Q1 - 2023
[6 empty] | Should have | Q2 - 2023
[6 empty] | Could have | Q3 - 2023
[6 empty] | Won't have | Q4 - 2023
Q1 - 2024
Q2 - 2024
Q3 - 2024
Q4 - 2024
Q1 - 2025
Q2 - 2025
Q3 - 2025
Q4 - 2025

## Projects and workstreams
Stakeholders
Category | Solution # | Sub-category | Strategic goal | Action Plan | KPI | Priority MoSCoW | Estimated deadline | R responsible | A accuntable | C consulted | S Support | I informed | Status
Projects | 4 | V | Waste Reduction | Paper usage policy
Guidelines for events/materials purchased/disposal
Hand dryers/alternative to paper towels
Domestic waste reduction (placement of bins + add posters)
|  |  |  | Measurement of annual waste | [8 empty] | Ongoing
|  |  |  | Digitalization measures | [8 empty] | Pending
|  | W | Energy Efficiency | Energy audit followed by installation of recommendations (sensor lights in meeting rooms, canteen and bathrooms) | 5,570 tCO2e to 2,785 tCO2e in 2030 (electricity)
Energy saving guidelines (ie. turning off computer, limiting double screens)
Heating standardization limit in winter in meeting rooms and canteen (19 degrees)
|  | X | Renewable Energies | Solar Cells on roof of Strandlodsvej 44 from 2024 | [8 empty] | Delayed to 2025
Exploration of other possibilities for energy saving/using renewable energy
|  | y | Sustainable Transport | Sustainable travel policy | 34,59 tCO2e to 17.29 tCO2e in 2030
Positive travel incentives, ie. rejsekort deducted through taxes
|  | Z | Sustainable Procurement | Sustainability embedded in new procurement policy
Conduct spend analysis to define high impact/low effort categories
Questionnaire to vendors on sustainability goals + define how important MSF DK portfolio is to them. Then either changing providers or strengthening collaboration. Identified so far: catering company (vegetarian)
|  |  | Certifications | Investigate if relevant.