## Strategy and Governance
Stakeholders
Category | Solution # | Sub-category | Strategic goal | Action Plan | Priority MoSCoW | Estimated deadline | R responsible | A accountable | C consulted | I informed | Green team activity lead | Status
Strategy & Governance | 1 | x | Internal governance | Define which positions need to be involved to ensure ownership of implementing initiatives to reduce the MSFSE carbon footprint. | Must have | Q4 2023 | Green Team | MT | All managers | All staff
|  |  |  | Do a stakeholder map (use travel policy as a pilot, categorize stakeholders based on their role and how we prioritize them) |  | Q4 - 2023 |  |  |  |  | Malin/ Azadeh | Done
|  |  |  | Do a communication plan based on the stakeholder map (why, who, when and in what way) |  | Q2 2024 | [5 empty] | Standby
|  |  |  | Do a force field analysis (driving and restraining forces, system limits possibly, intiatives in FR for ex for regional meetings, compile best practices) |  | Q3 2024 | [5 empty] | Standby
|  |  |  | Create a decision tree to clarify who decides what and the delegation of responsibility and accountability. |  | Q3 2024 | [5 empty] | Standby
|  |  |  | Update the Green team ToR |  | 2023-09-01 |  |  |  |  | Malin/Gaya | Done
|  |  |  | Formulate a revised set up based on learnings from other sections and share proposal with Oliver/MT. Learning from MSF Germany is to base setup on those areas that contribute the most to the footprint. So setup to be defined once 2023 footprint is calculated. |  | Q2 2024 |  |  |  |  | Malin | Ongoing
|  |  |  | Decide on format for Environmental roadmap action plan to be included in the CAP 2024-2025. |  | 2023-09-01 |  |  |  |  | Malin | Cancelled
|  |  | Environmental policy framework | No need to update the policies at this time, but need to make sure they are followed. Mapping compliance with travel policy could be a first step. | Should have |  | HR shared service manager | HR Director | HR admin support and BPR-Platform | All staff | HR rep (TBD) | Standby
|  |  |  | Contribute to the Environmental Care Travel Working Group and identify outcomes that are possible to implement in MSF Sweden. |  | Q2 2024 |  |  |  |  | Malin | Ongoing
|  |  | Monitoring and evaluating | Define how to monitor and evaluate​ the MSFSE footprint. The Environmental Impact toolkit will continue to be used. 2024-04: New template with financial and physical data to be used for 2023 and 2019 footprint. | Should have | Q2 2024 | Malin | MT | Climate Smart team | All staff | Malin | Ongoing
Note on M3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Done Ongoing Pending Standby Cancelled

## Network and relationships
Stakeholders
Category | Solution # | Sub-category | Strategic goal | Action Plan | Priority MoSCoW | Estimated deadline | R responsible | A accountable | C consulted | I informed | Green team activity lead | Status
Network & relationships | 2 | x | Information sharing | Internal communication plan. (Raluca has shared a CIF template with Malin to support) | Could have | [6 empty] | Standby
|  |  |  | External communication – keep page on website updated.​ (Update July 2023: quick update done. Bigger update planned for 2024) | Could have | [5 empty] | Malin | Done
|  |  |  | Info meeting 20 Dec 2023: Liselott to draft a ppt on some updates from the Green team, Karin and Gaya to prepare the presentation | Could have | [5 empty] | Gaya and Karin | Done
|  |  |  | Green team featured at Info meeting June 12, 2024 | Could have | [6 empty] | Ongoing
|  |  | Community building | Linking with other Green teams – monthly Nordic meetings planned. | Could have | [5 empty] | Malin | Ongoing
|  |  |  | Using resources more efficiently is important. Strengthening the Nordic Collaboration could be one way to reduce duplication of efforts. ACTION: Malin will reach out to MSF DK and MSF NO to see what topics we could work on together (more hands on) during 2024. For ex, every other monthly Nordic Green team meeting could be a working meeting where we work together on specific topics. | Could have | 2024-02-08 |  |  |  |  | Malin | Done (working session on footprint planned for Q2)
|  |  | Make use of current corporate partnerships | Mapping of corporate partnerships, to see if anyone might be able to support​ | Could have | [6 empty] | Standby
Note on M3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Done Ongoing Pending Standby Cancelled

## Education and Training
Stakeholders
Category | Solution # | Sub-category | Strategic goal | Action Plan | Priority MoSCoW | Estimated deadline | R responsible | A accountable | C consulted | I informed | Green Team activity lead | Status
Education and training | 3 | x | Climate & health literacy and awareness​ | See if Paediatric days and other projects connected to MSF Sweden could include module on climate & health. | Could have | [6 empty] | Standby
|  |  |  | Plan for an Ops connectivity presentation during the fall 2024 where the adaptation and advocacy part of MSFs work on planetary health is presented to all staff. | Should have | Q3-Q4 2024 | [5 empty] | Ongoing
|  |  | Enabling behaviour change | (Linked to monitor and evaluate) When we have data compiled use it in order to support behaviour change by showing it, for example through a training. On office and departmental levels.​ | Should have | Q2 - 2024 | Malin | MT | Climate Smart (Faith and Raluca) and L&D Adviser | All staff | Malin (identify another person for transparency) | Standby
|  |  |  | We want to communicate better to the office how the Green team contributes to the movement vision ACTION: Update Green team site on Intranet so that it links the MSF SE Environmental Roadmap to the vision the MSF movement has.- (drafted an updated page, to be updated 2024-03-06) | Should have | Q1 2024 |  |  |  |  | Gaya & Malin | Done
|  |  |  | Bachelor thesis on change management, project with Louise Linnander during the spring 2024. | Could have | Q1-Q2 2024 |  |  |  |  | Malin M | Ongoing
|  |  | HR policies, onboarding, L&D budget | Talk to L&D officer about how trainings on environmental sustainability could be done as part of the L&D activities for MSF Sweden. | Should have |  | L&D Adviser | HR Director | Climate Smart/Raluca | All staff | HR rep (TBD) | Standby
|  |  |  | Ask L&D officer if it is possible to add environmental sustainability to the onboarding in MSF Sweden. | Should have |  | L&D Adviser | HR Director | Climate Smart/Raluca | All staff | HR rep (TBD) | Standby
Note on F3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Must have Should have Could have Won't have
Note on M3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Done Ongoing Pending Standby Cancelled

## Projects and programs
Stakeholders
Category | Solution # | Sub-category | Strategic goal | Action Plan | Priority MoSCoW | Estimated deadline | R responsible | A accountable | C consulted | I informed | Green Team activity lead | Status
Projects & Programs | 4 | x | Measure and reduce paper usage's impact on the MSFSE carbon footprint | Reduce amount of paper used for FR campaigns. Use similar approach as MSF Germany - link to paper workshop pre-reading and summary | Should have |  | Marketing Unit Manager, KAM Unit Manager, Loyalty & Insights Unit Manager | FR Director | MSF Germany | All staff | Lisa | Standby
|  | y | Measure and reduce suppliers impact on the MSFSE carbon footprint | Understand which are the suppliers that have the biggest impact and include their impact in our footprint calculation. Use list of suppliers (which Internal Controller has) to identify top suppliers. | Should have |  | Internal controller | Support Director | Climate Smart (MSPP) | All staff | Malin | Standby
|  | z | Inspire staff to reduce, reuse and recycle | Communicate to all staff the setup of the new "Reduce, Reuse, Recycle" channel. | Should have | Aug 2023 | - | - | - | - | Gaya | Done
|  |  |  | Finalize the setup for the clothes library so that it can be communicated with all staff in conjunction with the clothing swap. | Should have | Sept 2023 | - | - | - | - | Gaya/Lisa/Karin | Done
|  |  |  | Send out the invitation to all staff and share info on the setup of the clothes swap with all staff. | Should have | Sept 2023 | - | - | - | - | Gaya/Lisa/Karin | Done
|  |  |  | Re-launch the reduce, reuse, recycle channel with a new name "sharing is caring" and a post in the General channel to market the channel to be used for more things that just reusing and recycling. UPDATE: The channel has not been re-launched. We need to socialize the channel when we re-launch it. UPDATE 2024-05-21: Malin will send ticket to IT to rename channel and will then post something in General channel to market the Sharing is caring channel. | Should have | May 2024 |  |  |  |  | Malin | Ongoing
|  |  |  | Follow up the clothes library, close the winter library and re-launch with a spring library. UPDATE 2024-04-23: Has been linked to "the office group", the working group on office environment. UPDATE 2024-05-21: The Green team will not re-launch the clothes library now. The suggestion is that it is part of the changes to the quiet room that the office group is working on. | Should have | May 2024 |  |  |  |  | Gaya/Lisa | Standby
Note on F3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Must have Should have Could have Won't have
Note on M3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Done Ongoing Pending Standby Cancelled
Note on H4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: We have a new structure where we work in different Teams, so the Teams should be the responsible ones maybe and not the unit managers.

## PLAN
| Strategy | Network | Education | Projects | SEP | OKT | NOV | DEC
Cykelutmaning |  | X
Clothing library |  | X | X
Event clothes swap |  | X
Present info meeting | X | X
Speaker |  | X